## Planned Burndown Chart
PLANNED BURNDOWN CHART
BACKLOG TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
#11 - As Head Researcher, I need an interface that is easy to read, so that I am able to analyse data without complication. 14 Story Points. | 14
Setup logn and Create account page | 1.5 |  |  |  | 1.5
Setup home page | 1.5 |  |  |  | 1.5
Setup design so it meets the "easy to read" requirement. | 4 |  |  |  |  | 4
Setup Jekyll so the components of the website are modular. | 4 | [5 empty] | 3 | 1
Make the website hosted on the server and have continuous integration for Jekyll to work | 3 | [6 empty] | 2 | 1
Story Point #9 - As Head Researcher, I need a place to store answers so that I can access the answers of the participants. 8 Story Points. | 8
Make the obvious tables as required. | 2 |  |  |  | 2
Make the tables handle multiple choice. | 1 |  |  |  |  | 1
Populate the tables | 2 | [5 empty] | 2
Make different vews for different users of the system. | 3 | [6 empty] | 1 | 2
Story Point #3 - As Head Researcher, I need the questionnaire to be able to contain questions with different types of input so that a variety of data can be gathered. 1 Story Point. | 1
Research how to implement different types of data input into the form | 0.33 |  |  |  | 0.25
Research how to do "select all that apply" questions in the form. | 0.33 |  |  |  | 0.25
Create the PHP for it. | 0.33 |  |  |  |  | 0.5
As Head Researcher, I need the questions to be directly linked to the database so that I know all answers entered have been saved. 7 story points. | 7
Create PHP that can handle multiple questionnaire's | 2 |  |  |  | 2
Make it so questions are pulled from the database to make a questionnaire. | 2 |  |  |  |  | 2
Make the it so questionnaire responses will be sent to the database with it's own unique ID. | 4 | [5 empty] | 2 | 2 | 2
TOTAL |  |  |  | 8 | 7.5 | 7.5 | 7 | 6 | 5 | 0

## Actual Burndown Chart
PLANNED BURNDOWN CHART
BACKLOG TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
#11 - As Head Researcher, I need an interface that is easy to read, so that I am able to analyse data without complication. 14 Story Points. | 14
Setup login, Home Create account page | 1.5 | Stewart |  |  | 0.75 | 0.75
Setup home page | 1.5 | Momchil |  |  | 0.75 | 0.75
Setup design so it meets the "easy to read" requirement. | 4 | Momchil |  |  | 2 | 2
Setup Jekyll so the components of the website are modular. | 4 | Momchil |  |  |  |  | 4
Make the website hosted on the server and have continuous integration for Jekyll to work | 3 | Momchil
Story Point #9 - As Head Researcher, I need a place to store answers so that I can access the answers of the participants. 8 Story Points. | 8
Make the obvious tables as required. | 2 | Jordan, Mikolaj, Aldrin |  |  | 2
Make the tables handle multiple choice. | 1 | Jordan, Mikolaj, Aldrin |  |  |  | 2
Populate the tables | 2 | Jordan, Mikolaj, Aldrin |  |  |  | 2
Make different views for different users of the system. | 3 | Jordan, Mikolaj, Aldrin |  |  |  |  | ? | ? | ?
Story Point #3 - As Head Researcher, I need the questionnaire to be able to contain questions with different types of input so that a variety of data can be gathered. 1 Story Point. | 1
Research how to implement different types of data input into the form | 0.33 | Bruce |  |  | 0.25
Research how to do "select all that apply" questions in the form. | 0.33 | Bruce |  |  | 0.25
Create the PHP for it. | 0.33 | Bruce |  |  | 0.5
As Head Researcher, I need the questions to be directly linked to the database so that I know all answers entered have been saved. 7 story points. | 7
Create PHP that can handle multiple questionnaire's | 2 | Jordan |  |  |  | 2
Make it so questions are pulled from the database to make a questionnaire. | 2 | Jordan |  |  |  | 2
Make the it so questionnaire responses will be sent to the database with it's own unique ID. | 4 | Jordan |  |  |  |  | 2 | ? | ?
TOTAL |  |  |  | 8 | 6.5 | 11.5 | 6 | 0 | 5 | 0

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.