## Planned Burndown Chart
PLANNED BURNDOWN CHART
BACKLOG TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
As a Lab Manager/Head Researcher, I need the ability to manage all permissions in the system, so i can manage access to experiments #82 | 1 | tbd
Lab Manager can alter permissions for co-researchers | 0.33 |  |  |  | 0.33
co-researchers can only access permitted pages | 0.33 |  |  |  |  | 0.33
an interface that allows this be done without having to access the database directly | 0.33 | [5 empty] | 0.33
As a Head Researcher, I should have the ability to make a new questionnaires from the front-end so that I can gather both qualitative and quantative data #69 | 18 | Momchil, Aldrin, Jordan.
The ability to phrase questions for the participant to answer | 3 |  |  |  | 3
The ability to add radio buttons. | 3 |  |  |  | 3
the ability to add numbers and text | 3 |  |  |  |  | 3
the ability to choose from a list of answers | 3 | [5 empty] | 3
the ability to choose multiple answers from a list | 3 | [6 empty] | 3
the questions and options appear as expected | 3 | [7 empty] | 3
As a Lab Manager/Head Researcher, I need the ability to manage all other users in a system so that I can manage their accounts. #81 | 8 | Bruce
the ability to add researchers | 1 |  |  |  | 1
the ability change passwords, | 1 |  |  |  |  | 1
the ability to delete researchers | 1 |  |  |  | 1
the ability to alter email addresses | 1 |  |  |  |  | 1
the ability to change researcher's details | 1 | [5 empty] | 1
an interface that allows this be done without accessing the database directly | 3 | [6 empty] | 1.5 | 1.5
As a Co-Researcher, I should be able to view experiments I have been assigned to so that I can aid in the research. #60 | 2
Create a specific co researcher view | 0.5 |  |  |  | 0.5
Creating a stored procedure which returns all the questionnaire which belongs to a particular co-researcher | 0.5 |  |  |  |  | 0.5
Display all the questionnaire to which researcher they belong to | 0.5 | [5 empty] | 0.5
co-researcher can see their experiments | 0.5 | [6 empty] | 0.5
As a Principal Researcher, I should be able to view the results of my experiments. #59 | 5 | Mikolaj
Create A procedure to fetch responses to a given questionnaire | 2 |  |  |  | 1 | 1
Display all the questionnaires and which researcher they belong to | 1 | [5 empty] | 1
Creating a stored procedure which returns all the questionnaires which belongs to a particular researcher | 1 | [6 empty] | 1
Researcher can see the results of their experiment | 1 | [7 empty] | 1
As Head Researcher, I need to be able to view individual responses to the questionnaire, so i can examine the data closely #34 | 2 | tbd
Grab the questions from a participant’s response | 0.5 |  |  |  | 0.5
Grab the answers from a participant’s response | 0.5 |  |  |  |  | 0.5
Data Displayed in a readable format | 1 | [5 empty] | 0.5
0.5
As a Lab Manager/Head Researcher, I should be able to view all experiments so that I can analyse all of the data. #80 | 1 | tbd
DB Procedure to show responses for specified questionnaire. | 0.33 |  |  |  | 0.33
Head Researcher can view an experiment | 0.33 |  |  |  |  | 0.33
Head Researcher can view all experiments | 0.33 | [5 empty] | 0.33
As a Head Researcher, I need to be able to export the data as a CSV file so that I can store the results locally on my computer. #8 | 2 | Mohammed
create an export button | 0.5 |  |  |  | 0.5
export button exports data | 1 |  |  |  | 0.5 | 0.5
exported data can be read | 0.5 |  |  |  |  | 0.5
As Head Researcher, I need a mandatory consent form to be completed before participants complete the questionnaire so that they are fully informed of what is expected of them. #1 | 2 | Stewart
create a page with the consent information and confirm button and a tickbox. | 1 |  |  |  | 1
It then redirect to the questionnaire if button pressed (maybe can be done for bootstrap or java). | 1 |  |  |  |  | 1
TOTAL |  |  |  |  | 12.66 | 9.33 | 6.33 | 6.5 | 5.5

## Actual Burndown Chart
ACTUAL BURNDOWN CHART
BACKLOG TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
As a Head Researcher, I should have the ability to make a new questionnaires from the front-end so that I can gather both qualitative and quantative data #69 | 18 | Momchil, Aldrin, Jordan.
The ability to phrase questions for the participant to answer | 3 |  |  |  | 1.5 | 1 | 0.5
The ability to add radio buttons. | 3 |  |  |  | 1.5 | 1 | 0.5
the ability to add numbers and text | 3 |  |  |  | 1.5 | 1 | 0.5
the ability to choose from a list of answers | 3 |  |  |  | 1.5 | 1 | 0.5
the ability to choose multiple answers from a list | 3 |  |  |  | 1.5 | 1 | 0.5
the questions and options appear as expected | 3 |  |  |  | 1.5 | 1 | 0.5
As a Lab Manager/Head Researcher, I need the ability to manage all other users in a system so that I can manage their accounts. #81 | 8 | Bruce
the ability to add researchers | 1 |  |  |  | 0.5 | 0.5
the ability change passwords, | 1 |  |  |  | 0.5 | 0.5
the ability to delete researchers | 1 |  |  |  | 0.5 | 0.5
adding new logins | 1
the ability to change researcher's details | 1 |  |  |  |  | 1
the ability to do have an interface which operates this. | 3 |  |  |  |  | 3
As a Co-Researcher, I should be able to view experiments I have been assigned to so that I can aid in the research. #60 | 2 | tbd
Create a specific co researcher view | 0.5
Creating a stored procedure which returns all the questionnaire which belongs to a particular co-researcher | 0.5
Display all the questionnaire to which researcher they belong to | 0.5
co-researcher can see their experiments | 0.5
As a Principal Researcher, I should be able to view the results of my experiments. #59 | 5 | Mikolaj
Create A procedure to fetch responses to a given questionnaire | 2 |  |  |  | 2
Display all the questionnaires and which researcher they belong to | 1 |  |  |  | 1
Creating a stored procedure which returns all the questionnaires which belongs to a particular researcher | 1 |  |  |  |  | 1
Researcher can see the results of their experiment | 1 |  |  |  |  | 1
As Head Researcher, I need to be able to view individual responses to the questionnaire, so i can examine the data closely #34 | 2 | tbd
Grab the questions from a participant’s response | 0.5
Grab the answers from a participant’s response | 0.5
Data Displayed in a readable format | 1
As a Lab Manager/Head Researcher, I should be able to view all experiments so that I can analyse all of the data. #80 | 1 | tbd
DB Procedure to show responses for specified questionnaire. | 0.33
Head Researcher can view an experiment | 0.33
Head Researcher can view all experiments | 0.33
As a Head Researcher, I need to be able to export the data as a CSV file so that I can store the results locally on my computer. #8 | 2 | Mohammed
create an export button | 0.5 |  |  |  | 0.5
export button exports data | 1 |  |  |  | 0.33 | 0.33 | ?
exported data can be read | 0.5 |  |  |  |  | 0.25 | ?
As Head Researcher, I need a mandatory consent form to be completed before participants complete the questionnaire so that they are fully informed of what is expected of them. #1 | 2 | Stewart
create a page with the consent information and confirm button and a tickbox. | 1 |  |  |  | 1
It then redirect to the questionnaire if button pressed (maybe can be done for bootstrap or java). | 1 |  |  |  |  | 1
TOTAL

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.