## Planned Burndown Chart
PLANNED BURNDOWN CHART
BACKLOG TASK | STORY POINTS | ASSIGNED TO | STATUS | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
As a Lab Manager/Head Researcher, I need the ability to manage all permissions in the system, so i can manage access to experiments #82 | 1 | Aldrin
Lab Manager can alter permissions for co-researchers | 0.33 |  |  | 0.33
co-researchers can only access permitted pages | 0.33 |  |  |  | 0.33
an interface that allows this be done without having to access the database directly | 0.33 |  |  |  |  | 0.33
As a Head Researcher I would like to create a questionnaire with open answered questions so that I can gather qualitative data. #94 | 6 | Momchil, Aldrin, Jordan.
A researcher is able to create a questionnaire | 1.5 |  |  |  | 1.5
Questionnaires can be created with custom titles | 1.5 |  |  | 1.5
The ability to create a question in which the user provides an open answer to with a text box | 1.5 |  |  |  |  | 1.5
The questions and options appear as expected | 1.5 | [5 empty] | 1.5
As a Head Researcher I would like to create a questionnaire with questions with fixed choice answers so that I can gather quantitative data. #95 | 12 | Momchil, Aldrin, Jordan.
A researcher is able to create a questionnaire | 2 |  |  | 2
Questionnaires can be created with custom titles | 2 |  |  | 1 | 1
The ability to create a question in which the user ticks from one of the provided options | 2 |  |  |  | 2
The ability to create a question in which the user ticks from multiple of the provided options | 2 |  |  |  |  | 2
The ability for the creator to specify the options | 2 | [5 empty] | 2
Validation to ensure that the user cannot enter duplicate options | 1 | [6 empty] | 1
The questions and options appear as expected | 1 | [6 empty] | 1
As a Lab Manager/Head Researcher, I need the ability to manage all other users in a system so that I can manage their accounts. #81 | 8 | Bruce, Aldrin
the ability to add researchers | 1 |  |  | 1
the ability change passwords, | 1 |  |  |  | 1
the ability to delete researchers | 1 |  |  | 1
the ability to alter email addresses | 1 |  |  |  | 1
the ability to change researcher's details | 1 |  |  |  |  | 1
an interface that allows this be done without accessing the database directly | 3 | [5 empty] | 1.5 | 1.5
As a Co-Researcher, I should be able to view experiments I have been assigned to so that I can aid in the research. #60 | 2 | tbd
Create a specific co researcher view | 0.5 |  |  | 0.5
Creating a stored procedure which returns all the questionnaire which belongs to a particular co-researcher | 0.5 |  |  |  | 0.5
Display all the questionnaire to which researcher they belong to | 0.5 |  |  |  |  | 0.5
co-researcher can see their experiments | 0.5 | [5 empty] | 0.5
As a Principal Researcher, I should be able to view the results of my experiments. #59 | 5 | Mikolaj
Create A procedure to fetch responses to a given questionnaire | 2 |  |  | 1 | 1
Display all the questionnaires and which researcher they belong to | 1 |  |  |  |  | 1
Creating a stored procedure which returns all the questionnaires which belongs to a particular researcher | 1 | [5 empty] | 1
Researcher can see the results of their experiment | 1 | [6 empty] | 1
As Head Researcher, I need to be able to view individual responses to the questionnaire, so i can examine the data closely #34 | 2 | Mikolaj
Grab the questions from a participant’s response | 0.5 |  |  | 0.5
Grab the answers from a participant’s response | 0.5 |  |  |  | 0.5
Data Displayed in a readable format | 1 |  |  |  |  | 0.5
0.5
As a Lab Manager/Head Researcher, I should be able to view all experiments so that I can analyse all of the data. #80 | 1 | Mikolaj
DB Procedure to show responses for specified questionnaire. | 0.33 |  |  | 0.33
Head Researcher can view an experiment | 0.33 |  |  |  | 0.33
Head Researcher can view all experiments | 0.33 |  |  |  |  | 0.33
As a Head Researcher, I need to be able to export the data as a CSV file so that I can store the results locally on my computer. #8 | 2 | Mohammed, Aldrin
create an export button | 0.5 |  |  | 0.5
export button exports data | 1 |  |  | 0.5 | 0.5
exported data can be read | 0.5 |  |  |  | 0.5
As Head Researcher, I need a mandatory consent form to be completed before participants complete the questionnaire so that they are fully informed of what is expected of them. #1 | 2 | Stewart
create a page with the consent information and confirm button and a tickbox. | 1 |  |  | 1
It then redirect to the questionnaire if button pressed (maybe can be done for bootstrap or java). | 1 |  |  |  | 1
As a participant, I should be able to access the questionnaire via a link so that I can easily access the questionnaire to complete it. #24 | 2 | Jordan, Aldrin
Each questionnaire should be accessible using it's ID in the URL. | 1 |  |  |  |  | 1
TOTAL |  |  |  | 11.16 | 11.16 | 8.16 | 7 | 4.5

## Actual Burndown Chart
ACTUAL BURNDOWN CHART
BACKLOG TASK | STORY POINTS | ASSIGNED TO | STATUS | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
As a Lab Manager/Head Researcher, I need the ability to manage all permissions in the system, so i can manage access to experiments #82 | 1 | Aldrin
Lab Manager can alter permissions for co-researchers | 0.33 |  | working on it |  |  | 0.33
co-researchers can only access permitted pages | 0.33 | [5 empty] | 0.33
an interface that allows this be done without having to access the database directly | 0.33 | [6 empty] | 0.33
As a Head Researcher I would like to create a questionnaire with open answered questions so that I can gather qualitative data. #94 | 6 | Momchil, Aldrin, Jordan.
A researcher is able to create a questionnaire | 1.5 |  |  | 0.75 |  | 0.75
Questionnaires can be created with custom titles | 1.5 |  |  | 1.5
The ability to create a question in which the user provides an open answer to with a text box | 1.5 |  |  |  | 0.75 | 0.75
The questions and options appear as expected | 1.5 |  |  |  | 0.75 | 0.75
As a Head Researcher I would like to create a questionnaire with questions with fixed choice answers so that I can gather quantitative data. #95 | 12 | Momchil, Aldrin, Jordan.
A researcher is able to create a questionnaire | 2 |  |  | 1 |  | 1
Questionnaires can be created with custom titles | 2 |  |  | 1 | 1
The ability to create a question in which the user ticks from one of the provided options | 2 |  |  |  | 1 | 1
The ability to create a question in which the user ticks from multiple of the provided options | 2 |  |  |  | 1 | 1
The ability for the creator to specify the options | 2 |  |  | 1 | 1
Validation to ensure that the user cannot enter duplicate options | 1 |  |  |  |  | 1
The questions and options appear as expected | 1 |  |  |  |  | 1
As a Lab Manager/Head Researcher, I need the ability to manage all other users in a system so that I can manage their accounts. #81 | 8 | Bruce, Aldrin
the ability to add researchers | 1 |  |  | 0.5 | 0.5
the ability change passwords, | 1 |  |  | 0.5 | 0.5
the ability to delete researchers | 1 |  |  | 0.5 | 0.5
the ability to alter email addresses | 1 |  |  |  |  | 1
the ability to change researcher's details | 1 |  |  |  | 1
an interface that allows this be done without accessing the database directly | 3 |  |  |  | 1 | 1 | 1
As a Co-Researcher, I should be able to view experiments I have been assigned to so that I can aid in the research. #60 | 3 | tbd
Create a specific co researcher view | 0.5
Creating a stored procedure which returns all the questionnaire which belongs to a particular co-researcher | 0.5
Display all the questionnaire to which researcher they belong to | 0.5
co-researcher can see their experiments | 0.5
As a Principal Researcher, I should be able to view the results of my experiments. #59 | 5 | Mikolaj
Create A procedure to fetch responses to a given questionnaire | 2 |  |  | 2
Display all the questionnaires and which researcher they belong to | 1 |  |  | 1
Creating a stored procedure which returns all the questionnaires which belongs to a particular researcher | 1 |  |  |  | 1
Researcher can see the results of their experiment | 1 |  |  |  | 1
As Head Researcher, I need to be able to view individual responses to the questionnaire, so i can examine the data closely #34 | 2 | Mikolaj
Grab the questions from a participant’s response | 0.5 |  |  |  | 0.5
Grab the answers from a participant’s response | 0.5 |  |  |  | 0.5
Data Displayed in a readable format | 1 |  |  |  | 0.5 | 0.5
As a Lab Manager/Head Researcher, I should be able to view all experiments so that I can analyse all of the data. #80 | 1 | Mikolaj
DB Procedure to show responses for specified questionnaire. | 0.33 |  |  | 0.33
Head Researcher can view an experiment | 0.33 |  |  |  | 0.33
Head Researcher can view all experiments | 0.33 |  |  |  | 0.33
As a Head Researcher, I need to be able to export the data as a CSV file so that I can store the results locally on my computer. #8 | 2 | Mohammed, Aldrin
create an export button | 0.5 |  |  | 0.5
export button exports data | 1 |  |  | 0.33 | 0.33 | 0.33
exported data can be read | 0.5 |  |  |  | 0.25 |  | 0.25
As Head Researcher, I need a mandatory consent form to be completed before participants complete the questionnaire so that they are fully informed of what is expected of them. #1 | 2 | Stewart
create a page with the consent information and confirm button and a tickbox. | 1 |  |  | 1
It then redirect to the questionnaire if button pressed (maybe can be done for bootstrap or java). | 1 |  |  |  | 0.33 | 0.33 | 0.33
As a participant, I should be able to access the questionnaire via a link so that I can easily access the questionnaire to complete it. #24 | 1 | Jordan, Aldrin
Each questionnaire should be accessible using it's ID in the URL. | 1 |  |  |  |  | 1
TOTAL | 43 |  |  | 11.91 | 14.07 | 11.74 | 1.91 | 0.33

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.